Viridian

To:	CEEB

From:	Kim Oswald, on Behalf of the CEEB Evaluation Committee

Date: 	March 5, 2010

RE:	Evaluation Committee Status Report – for March 10 Meeting

## Residential Studies

### Home Energy Solutions Impact Evaluation - CT

This study will examine the impacts of gas and electric measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study will focus primarily on measures or groups of measures with the largest savings potential and that also have not been examined through other studies.

Nexant is the contractor for this evaluation.  The kickoff meeting was held on May 12. Currently, the Contractor has formed the sample using a review of the program records to determine an appropriate sampling frame. Nexant has completed all site visits (32 in CL&P and 9 in UI areas).    Energy Savings analysis for each site is underway using whole house engineering models.

Nexant is now collecting customer billing data for participants and matched samples of non-participants.  There have been some logistical issues with matching electric utility accounts with the corresponding gas company accounts.  Those problems now appear to have been resolved in a reasonable manner. These delays will delay provision of final results.    The project also includes interviews with HES vendors.  Those interviews are currently being scheduled. The Table below reflects the study schedule with delays noted.

This study will support ISO requirements.

| Timeline | Original Date | Reason for Delay | New Date |
| --- | --- | --- | --- |
| Kick-Off Meeting | May 12, 2009 |  | May 12, 2009 |
| Program Data Request | May 26, 2009 |  | May 26, 2009 |
| Program Participant Data Provided | July 31, 2009 |  |  |
| Draft Workplan | 2 weeks after participant data received | Completed in absence of data to avoid study delays | July 10, 2009 |
| Final Workplan | 1 week after draft approved -Draft Approved Aug 3 |  | August 7, 2009 |
| Contracts and PO Signed | 2 weeks after Kickoff | Exceptions to confidentiality agreements and PSA delay | October 13, 2009 |
| 2007 Billing Data due from Utilities | September 26, 2009 | Missing Data | February 26, 2010† |
| 2009 Billing Data due from Utilities | January 29, 2010 | Missing Data | February 26, 2010† |
| Draft Savings Estimate – from Engineering Study | October 30, 2009 | Contract issues resulted in delay in completing site visits | March 26, 2010* |
| Draft Final Report | March 26,2010 | Missing Data | June 11, 2010* |
| Final Report | April 16, 2010 | Missing Data | June 30, 2010* |
| Final Presentation | TBD | Missing Data | TBD |
| *Date dependent on receiving 2007 – 2009 billing data for participant and non-participant sample groups by February 28, 2010. †Non-participant control group account lists delivered to Nexant on this date. Nexant will provide a stratified sample and request monthly utility billing data. |

### WRAP/UI Helps Impact Evaluation

The WRAP and UI Helps evaluation will examine savings rates and comprehensiveness of installations in participant homes for both electric and gas measures.    The contract was awarded to KEMA.  Three challenges arose in the early going.   It has been very difficult for the Contractor to determine what measures were recommended for installation to assess whether items were removed, never installed, or rejected by the owner (landlord or participant). The Contractor will do more on-site investigation to try to estimate the gaps.  Second, in many cases either the primary heating fuel or the account number for gas customers is missing from the databases.  The Contractor is removing these customers from the sample and replacing them with similar customers.  The large participant base should greatly reduce the potential for bias that one might normally expect from doing so.

Finally, and unsurprisingly, many program participants have moved since participating.  In many cases, the measures will still be in place at the original location.  However appliances owned by the participants probably left with the participants and may now be in another state.  The Contractor will need to replace this portion of the sample.

The contractor has completed all of the 92 site visits; data from all sites have been entered.    Lighting loggers remained in place through December in order to better measure winter peak savings. As of early February, all but a couple of lighting loggers were recovered – in those few cases, the resident has not been available for the pickup.  During February the Contractor anticipated completing the logger data analysis and beginning DOE-2 simulation work and calibration.

| Event/Deliverable | Due Date | New Date (if any) | Reasons |
| --- | --- | --- | --- |
| Kickoff Meeting | August 7, 2009 |  |  |
| Draft Work plan | August 25, 2009 |  |  |
| Work plan comments | September 8, 2009 |  |  |
| Final Work plan | September 15, 2009 |  |  |
| On-sites | Oct 1 – Dec 31, 2009 | Jan 20, 2010 | Extended logging period to better capture winter savings |
| Draft Report with Executive Summary | January 29, 2010 | March 19,2010 | See above |
| Report Comments | February 12, 2010 | 2 weeks after submission |  |
| Final Report Delivered | February 26, 2010 | 1 week after draft review |  |
| Presentation | TBD |  |  |

This study will support ISO requirements.

### CFL Saturation and Net to Gross Assessment

On June 1, the Companies were informed that the Department is interested in gaining more information on the extent to which current programs have transformed the market for Compact Fluorescent Lamps.  The scope of work combines and compares the experiences of other states with and without CFL programs, and also collects and analyzes information unique to Connecticut.  The results will inform development of program alternatives to capture remaining potential from common and specialized CFLs.

NMR was selected as Contractor for this project.  On a fast track, NMR has developed a workplan and provided surveys for 500 randomly selected customers and customers known to have purchased NCP program lamps.  NMR has developed instruments to use for in-home data collection and to elicit from customers the reasoning behind CFL saturation and location selection in about 100 Connecticut homes. Draft reports for both the regional analysis and the Connecticut sub-sample were provided on October 5.

The Connecticut Modeling report has been completed (as of February 5) and finds that CT still provides fertile ground for CFL program efforts.  The Connecticut Program report was delivered on March 3.  That portion of the overall study was delayed by difficulties in acquiring data on the models of CFLs supported by CEEF programs.

A presentation of the study has been scheduled for the morning of the April 14 Board Meeting. Since a presentation was not originally included in the scope of work, an additional $4,500 will need to be added to the contract amount.  I have heard no objections from the Companies to altering the contracts to reflect that change.

## Commercial/Industrial Studies

### Energy Opportunities Impact Study

The Energy Opportunities Impact Evaluation will determine gross energy and demand savings realization rates, gross and net energy and demand savings, summer and winter coincidence factors, and annual hours of use for prescriptive measures installed through the EO program. The study uses on-site metering using data loggers, lighting loggers and hand held fixture wattage measurement devices to estimate these values.  This impact evaluation will look at the EO Program Year of 2008.

KEMA was selected to be the contractor for this study.  The initial kick-off meeting was held on June 2.  To date, the contractor has scheduled and performed site visits at 55 participant projects.  For each site, monitored data have been retrieved and data entered.  Lighting logger data have been retrieved and load shapes developed for all the projects that included lighting measures.

Saving analysis for non-lighting projects continues in parallel.   Complete savings analysis for all 25 non-lighting sites should be completed by the end of second week of February.  Analysis of all sample data and draft population impacts will be complete by the end of February.

The draft report is expected to be delivered in early March.

This study will support ISO requirements.

### Energy Conscious Blueprint Impact and Process Study

In order to quantify the benefits of efficient measures installed in commercial and industrial (C&I) facilities, through the Energy Conscious Blueprint (ECB) program, ISO-NE requires peak demand savings estimates for the ECB program.  As a step in developing those estimates, Contractors typically collect data that can be used to calculate hourly load shape data. The benefits include avoided capacity costs resulting from reduced electric demand during peak hours and avoided energy costs resulting from energy savings during seasonal and on/off-peak periods.

In addition to the impact study, changes in the program and in the market make plain the need for a process evaluation that will examine customer benefits realized, comprehensiveness and depth of installations made with and beyond program incentives and effects of individual measures on program performance.  The report will produce recommendations concerning how to best maintain program successes and improve program performance in terms of savings, customer benefits and elimination of lost opportunities.

The RFP for this study was released to approximately 20 vendors on March 4th.  Proposals are due on March 31st.

## Regional EM&V Forum – 2010

Please refer to the January 2010 EM&V Forum quarterly newsletter for a general update on Forum projects. Since issuing the newsletter, important updates on key projects include items referenced for Protocol Development projects A2 and A3 (above), and the following Research and Evaluation projects:

NEEP will provide further updates to the Forum participants at the next Project Committees teleconference on February 11.

### Load Shape Study – Phase 1 Completed

This regional study collected load shapes developed at other utilities for measures offered in New England, other states on the Eastern Seaboard and some Northwestern States.  In this two phase project, the contractor first assessed whether or not the load shapes reflect situations sufficiently comparable to those in the Northeast to enable us to use them in filings when utility-specific information is not yet available.  In Phase 2 the contractor will devise sampling plans, conduct on-site data collection efforts and analysis to obtain load and savings profiles (starting October 2009) for those identified measures of particular interest in each region.

The Contractor (KEMA) started working on this project on January 10, 2009.  The Phase 1 recommendations were provided on June 1st and reviewed by subcommittee members.  The report identifies existing load shape studies, gaps in data, and options for filling gaps both in the East and the Northwest.

EM&V Forum participants, guided by the EMV subcommittee, were asked to take additional steps of establishing the priority data needs within the Forum in order to finalize a scope of work and RFP for Load shape Project Phase 2.  As a group the membership decided that the highest priority areas for load shape development are for C&I Lighting and Unitary HVAC systems.

### Load Shape Estimation: C&I Lighting

This project involves the creation of a spreadsheet tool that can be used by members of the Regional EM&V Forum to calculate and quantify the hourly savings of efficient lighting measures installed at Commercial and Industrial facilities.

This project is just beginning.  Two contractors provided proposals on January 8.  KEMA was selected to complete the study.  Since that time, NEEP negotiated a revised scope and budget  with KEMA that reduced costs and better met our needs

### Load Shape Estimation:  C&I Unitary HVAC

The objective of the study is the development of Unitary HVAC load factor data for every hour of the calendar year. The annual load shape data must also be adaptable to different program participant populations located within the service territories of Forum members; load shape data will be weather-normalized in order to provide for the calculation of aggregate load shapes that reflect the weather conditions of different Program Administrator customer populations.

The Unitary HVAC Loadshape RFP was issued on January 14, with bids due on January 29. The subcommittee reviewed the HVAC bids on February 4.  The contractor selected was KEMA and the project will initiated as soon as possible.

### Glossary of Terms and Definitions Project

The project is on schedule, with a first draft of the glossary reviewed by the subcommittee and now undergoing expansion and some revisions.  Selected technical experts reviewed the second draft.

The NMRGroup team has researched existing state and regional energy efficiency reporting requirements and practices, and is identifying energy efficiency data needs to support both

State/regional environmental policies and energy planning systems. Their technique used interviews and secondary sources. The contractor will synthesize feedback and research in February 2010, and will develop final recommended energy efficiency reporting guidelines and a reporting template by the end of March 2010.

### C&I Lighting: Measure Persistence of Savings

The purpose of the project is to develop up-to-date impact parameters that describe lighting measure persistence, i.e. in place and operating over multiple (5+) years based on field and survey samples. The project will also develop equipment life estimates from secondary sources (manufacturer reports). The value of this project to sponsors is that commercial lighting is the largest source of savings for most EE providers in the region. Multi-year persistence lends itself to regional study because the research is difficult, expensive, and measures are consistent across locations.

The subcommittee selected a contractor for this project (KEMA) and a kick off meeting was held on October 16. The original schedule and work scope for this project were modified as a result of subcommittee review of the proposals. The project will now proceed as a phased effort, with the first phase being outreach to Project funders to establish what program data is available to develop the sampling strategy. The project will have several checkpoints at which the subcommittee and contractors can agree to proceed or suspend the effort depending on the availability of program data and the ability to develop an appropriate sample size and strategy.

Data collection and finalization of some individualized Non-disclosure Agreements between project administrators and KEMA (precursor to data collection that was needed by a few project administrators) are underway. The next subcommittee teleconference was held on February 4 to review the sample design and the status of the data collection effort.

### Common EM&V Methods and Savings Assumptions

KEMA, the contractor for this project, has conducted interviews with program administrators and EM&V experts regarding EM&V methods used to estimate/calculate savings for a set of priority measures or program types. KEMA has also completed its review and comparison of savings assumptions and algorithms for the priority set of measures.

Forum participants are currently reviewing draft reports. In February 2010, KEMA has developed guidelines for recommended EM&V methods and savings assumptions, including recommended levels of savings rigor, for Project Committee consideration and ultimately Steering Committee adoption.

As reported by NEEP, “The results of this project will inform two national M&V protocol discussions. The North American Energy Standards Board (NAESB) is currently convening subcommittees for its M&V project to address retail and wholesale M&V for energy efficiency. NEEP gave a presentation at a November NAESB meeting about how the EM&V Methods project can help inform NAESB’s efforts, and 2010 EM&V Forum funding will be used for NEEP to actively participate in the NAESB M&V project throughout the year. The National Action Plan for Energy Efficiency (NAPEE) is also engaged in a national EM&V project. NAPEE has conducted surveys to identify national EM&V needs and priorities and is working with a Technical Resource Group that includes many Forum participants to help focus its efforts. The findings from the EM&V Methods project will help inform the NAPEE project as it further refines the EM&V priority areas to be addressed on a national level.  A final report and guidelines from Project A2: EM&V Methods will be available in mid-2010.”

I am concerned about the direction of this project for several reasons.  First, the quality of the current document is poor.  The report is both poorly written and does not reflect the input of at least some of those interviewed.  Only a very narrow range of methods were offered and those offered reflect the current practice of the firm that wrote the report.  Many important issues, such as biased in methods and results, are ignored.  I believe the current version of the report is very narrow and not very useful.

More troubling to me is that NEEP plans to the final version of this document (which shall at least overcome the poor writing) to the Forum Steering Committee (Utility Commissioners from the states represented by the Forum).  When the report is provided, The Forum will ask the Steering Committee to adopt the presented methods in their states.  Should the DPUC decide to do so, it would crystallize methods to match one contractor’s views.  It could, but might not, result in the rejection of results obtained through methods not included in the document. Adopting a set of methods simplifies review of studies, but is unlikely to promote evaluation excellence.

### Common EE Reporting Guidelines

NMR reported its preliminary findings from air regulator interviews to date, review of current reporting practice, and reviewing system planner questions regarding energy efficiency data needs to the project subcommittee on January 27.

### Incremental Cost Study

Background materials provided by VEIC have been submitted to the subcommittee for review prior to discussion and development of a scope of work.