## Slide 1: 2023 Annual Legislative Report
November 8, 2023

## Slide 2: Timeline
July 2023
Development of draft ALR outline/content - Completed
November 2023
Cover and Internal Design for November EEB Meeting
December 2023
Chair letter & Executive Summary for EEB Review 12/1/23
December 2023
All content in layout (minus data) for EEB Review 12/13/23
March 1, 2024
ALR submitted to General Assembly

## Slide 3: Update
Letter from Chairs and Executive Summary in progress.
Consultant working on and end of year activities will impact.
Developed ALR cover options and layout and recommendation for Board.
Worked w/ EEB Secretary to update Board members, titles, and photos.
Residential drafted, C&I, and Community Outreach & Workforce sections in development
Full ALR layout expected 12/13/23
Companies compiling 2023 data
Final 2023 data available in mid-February, Companies will insert into ALR