****

**EEB Evaluation Committee Monthly Meeting**

**Monday April 9, 2018 – 10:00-11:30 - Meeting probably shorter**

Department of Energy and Environmental Protection – Public Utilities Regulatory Authority, Commissioner's Conference Room, OCC, 10 Franklin Sq., New Britain, CT

Meeting Materials in Box folder: <https://app.box.com/s/bmr1ug9gcffnj802c1t0ju8ang9m7wf1>

**Call-In Number: 303/900-3524; WEB Access:** [**www.uberconference.com/skumatz**](http://www.uberconference.com/skumatz)

*(Backup number – only if primary # doesn’t work –720/820-1390 Code (1st caller) 8296#*

[*www.join.me/SkumatzEconomics*](http://www.join.me/SkumatzEconomics)*)*

**COMMITTEE MEETING AGENDA - DRAFT**

1. Public Comment
2. Approval of Minutes from previous meetings 1 min
3. Non-Project Updates and Issues : 5 min
   1. Review Interim progress / highlights;
      * Interim e-votes and meetings (see bottom of agenda).
      * Upcoming kickoff and data meetings
      * Status of Data requests and deliverables / dates / upcoming (as needed)
   2. SERA team invoice - March
4. Discussion of Projects / Status (and data) – *see Gantt & Project summaries-* **updated** 30min
   1. Walk-though of Projects / Monthly Status Report – focus on Gantt “changes” and status of new projects; update on results of call / meeting on “new” steps for projects
      * Residential Projects (Skumatz & Wirtshafter)
      * C&I Projects (Chiodo & Jacobsen)
5. Other items –
   1. Update on DEEP / NEEP M&V 2.0 Grant or other projects.

\*\*\* Supporting Materials in Box folder and attached, including:

|  |  |
| --- | --- |
| * Updated Gantt Chart & Project Status Summary * E-votes / call notes (attached) * Data dates and progress (coming) | * Minutes from previous meeting * SERA Invoice |

***Summary of 2017-18 Votes To Date –***

Minutes & Invoices Approvals -

|  |  |  |
| --- | --- | --- |
| 2017 | Minutes for the month | SERA Invoice |
| Mar 2018 |  |  |
| Feb 2018 | HOLD – (O’Connor 3/14, Gorthala abstains 3/14; Melley 3/21) Need Dornbos | * PASSED – (O’Connor, Gorthala 3/14; Melley 3/21) |
| Jan 2018 | PASSED – (O’Connor, Gorthala 3/14; Melley 3/21) | * PASSED – (O’Connor, Gorthala 3/14; Melley 3/21) |
| Dec | December minutes –PASSED – (O’Connor and Dornbos 1/9; Gorthala Abstained not present 1/9, Deep approved to approve in 1/17/18 email with question / question answered). | * Invoice thru 12/13 - PASSED EVOTE / Distrib 12/13; In favor Dornbos, Gorthala, O’Connor 12/14. * Est invoice thru EOM – PASSED EVOTE (Distrib 12/21; In favor O’Connor and Gorthala 12/21; In favor Dornbos 12/22. |
| Nov | PASSED vote during meeting 12/11/17 (O’Connor / Melley / Gorthala) | PASSED vote during meeting 12/11/17 (O’Connor / Melley / Gorthala) |
| Oct | PASSED e-vote Melley (11/8), Dornbos (11/14), O’Connor (11/14, reiterating vote during meeting) | PASSED e-vote for Aug-Oct Invoices – Dornbos, O’Connor, Gorthala, Melley (11/14). |
| Sept | PASSED e-vote Melley, Dornbos, O’Connor 10/13; Gorthala 10/14. | See above |
| Aug | PASSED-e-vote O’Connor, Gorthala 9/11; Melley 9/12; Dornbos 9/19. | See above |
| July | PASSED-e-vote O’Connor, Gorthala 9/11; Melley 9/12; Dornbos 9/19. | PASSED e-vote O’Connor, Melley, Gorthala 9/13; Dornbos 9/19. |
| June | PASSED-e-vote O’Connor, Dornbos, Gorthala passed 7/10/17; Melley abstains (minutes too long, not always accurate) | PASSED-e-vote O’Connor, Dornbos, Gorthala passed 7/10/17 |
| May | PASSED-in meeting O’Connor, Gorthala, Melley (6/12/17) | PASSED-in meeting Gorthala, O’Connor, Melley (6/12/17) |
| April | PASSED-Evote Oconnor, Gorthala (5/31/17); re-sent 6/9; in favor Dornbos, Melley (6/12/17) | PASSED-Evote Oconnor, Gorthala (5/31/17); re-sent 6/9; in favor Dornbos, Melley (6/12/17) |
| March | PASSED-Evote O’Connor, Dornbos, Melley, Gorthala 4/13/17 | PASSED-Evote O’Connor, Dornbos, Melley, Gorthala 4/13/17 |
| February | PASSED-Evote O’Connor, Melley, Gorthala 3/9/17 | PASSED- Evote O’Connor, Melley, Gorthala (3/9/17) |
| January | E-vote O’Connor 2/6, Gorthala 2/6; re-sent out for third vote 7/10/17 | PASSED- Evote O’Connor, Melley, Gorthala (3/9/17) |

**Other Votes / Meetings / Tracking – TO BE UPDATED**

March 2018

* 3/

February 2018

* 2/6/18 – EA Team memo on viable project / oversight combinations

January 2018

* 1/25/18 – Review draft C1630 distributed
* 1/19/18 - EA Team Sent note to contractors on project status
* 1/17/18 – PASSED – Add $70K to budget for R1641 (discussion & memo in eval committee meeting). Votes via email: O’Connor 1/8/18; Dornbos 1/9/18; Melley 1/17/18; Gorthala abtain 1/9/18 (not at meeting).
* 1/9/18 – one pager for EEB Board summarizing Eval Rec’m for sweep prepared; delivered / discussed with EEB by Skumatz.
* 1/9/18 – Motion / Memo on Sweep Passed. EA Team memo on Eval Rec’m for sweep – Projects and EA team budget recommendation – BOTH PASSED by committee (O’Connor, Dornbos, Gorthala with clarifications, 1/9);
* 1/4/18 – Review draft R1613/14 distributed

December 2017

* 12/1 - HES Process and Impact Data meeting
* 12/11 - Memo (during meeting) reconfirming data cost allocations to projects (for utility notice), funds to draw temporarily from evaluation, authority for contractors to spend and re-submit invoices to utilities.
* 12/11 - Call between Skumatz /Swift on Sweep calculations / clarification of carryover treatments, etc.
* 12/11 – Vote in committee to augment budget of C1641 by $70K
* 12/12 - VOTE APPROVE sweep approach - O’Connor sent EA team budget sweep revised memo from 12/11 meeting to committee; in FAVOR of general recommendations / approach: O’Connor (12/12), Dornbos (12/13), Gorthala (12/13) with conditions (O’Connor - try to work with DEEP on 1663; Dornbos – approve overall compromise effort / approach with clarifications; Gorthala – agree with Dornbos / address DEEP issues); DEEP abstains but raises issues / questions.
* 12/13 – Skumatz responded to DEEP question.
* 12/13 - EEB meeting on Sweep – Skumatz attended via phone.
* 12/13 - Skumatz attended Residential committee meeting to monitor regarding evaluation / sweep
* 12/12 - Skumatz and Chiodo(?) attended Commercial Committee meeting to monitor regarding evaluation / sweep
* 12/19 – Call with utilities to understand / discuss elements of budget sweep (Skumatz and others)
* 12/20 - R1602 RNC report presentation

November 2017

* 11/2 – Kickoff NEI project (R1709)
* 11/13-DR pilots programs info (R&C)
* 11/14 – PASSED October minutes
* 11/14 – PASSED SERA invoice Aug-Oct
* 11/28 – Impromptu data call R1707/RNCNTG

October 2017

* 10/2 - Data Processes meeting
* 10/4 – Data call – R1707 (RNCNTG)
* 10/5 – Data call – R1706, R1616, R1705 (RASS, Lighting, MF)
* 10/5 – Kickoff R1702 (codes and standards)
* 10/13 – Evotes requested on minutes (passed; see table above)
* 10/13 –PASSED - C1630 budget increase of $5K (evote #2); In favor O’Connor 10/13, Dornbos 10/13; Melley no answer in 10/13 email; Gorthala abstain 10/14; Gorthala in favor 10/30.
* 10/16 – Data meeting NEI project (R1709)
* 10/20 – UI contracts approval process update meeting
* 10/30 – R1704 HES Programs update discussion

September 2017

* 9/5 – Discussion of UDRH
* 9/5 – Data request discussion 1706/1616/1705
  + - 9/21 - R1615 LED NTG Project Presentation
    - 9/22 - R1706 RASS Kickoff
    - 9/28 - R1707 RNC NTG Kickoff
    - 9/29 - R1606 Behavior Retention Project Presentation

August 2017

* 8/1 – Meeting on recommendations for PSD revisions to Residential HVAC measures – boilers, furnaces, HPWH, circulating pumps
* 8/9 – presentation to EEB on data costs issue
* 8/11- Data cost call
* 8/24-Data request meeting 1630
* 8/25-Data cost call

July 2017

* EEB full board vote on Data memo passed
* 7/31 – Meeting on recommendations for PSD revisions to Steam Trap equation
* 7/23 – Meeting on recommendations from 1602 on UDRH

June 2017

* Approved / Passed – Memo Summarizing Mini-RFP Results (in favor O’Connor, Dornbos, Gorthala, 6/5/17)
* Approved / Passed – 2 parts / both approved: Approving Memo identifying extra costs to evaluation projects because of data issues from utilities and identifying the assessment to each utility and recommending addition to each of the project budgets, with the money to be pulled out of funds that are not evaluation funds. (in favor O’Connor, Dornbos, Gorthala. 6/22/17)

May /June 2017

* None additional.

April 2017

* Interim Meeting -1617 DHP Working Group – 4/10/17

March 2017

* None additional

February 2017

* Approved/passed Evaluation Plan Update (votes in favor 2/8/17: O’Connor, Dornbos, Gorthala)

January 2017 Interim votes and interim committee meetings – not final

* Votes in favor of evaluation plan (in favor O’Connor & Gorthala 1/9/17; Dornbos 1/12 – passed). 1/24 DEEP votes against.
* December 2016 minutes passed (In favor 1/9 O’Connor, Melley, Gorthala, Dornbos).