Viridian

To:	ECMB

From:	Kim Oswald, on Behalf of the ECMB Evaluation Committee

Date: 	January 10, 2010

RE:	Evaluation Committee Status Report – for January 13 meeting

# Residential Studies

### Residential Central Air Conditioning – Regional - Complete

The Residential CAC study was intended to examine load shapes, coincidence factors and savings resulting from replacement of residential air conditioners.  This study is being done within the regional Evaluation Working Group.  In addition to working on the savings impacts of the programs across the region, Connecticut issued a separate contract to assess free-ridership  ADM Associates was selected to complete the study.  After numerous problems, errors and delays, the Contractor has produced a final report that is acceptable.  Both reports are complete.   I believe that they have also been filed.  ADM will present their results in a session prior to the meeting on 1/13/10

This study is intended to support ISO requirements.

### Home Energy Solutions Impact Evaluation - CT

This study will examine the impacts of gas and electric measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study will focus primarily on measures or groups of measures with the largest savings potential and that also have not been examined through other studies.

Nexant has been selected as contractor for this evaluation.  The kickoff meeting was held on May12. Currently, the Contractor has formed the sample using a review of the program records to determine an appropriate sampling frame. As of December 15, Nexant has completed 30 of 31 site visits in the CL&P service area and 3 of 9 sites visits in the UI area.  The last CL&P site visit was expected to be complete within that next week.  Remaining site visits will be completed in January.  Nexant is now collecting customer billing data for participants and matched samples of non-participants.  There have been some logistical issues with matching electric utility accounts with the corresponding gas company accounts.    Those problems now appear to have been resolved in a reasonable manner. However, there continues to be delays associated with collecting billing data for non-participating customers from one of the Companies due to backlogs in the programming department.  These delays may delay provision of final results.    The project also includes interviews with HES vendors.  Those interviews have not yet begun.

This study will support ISO requirements.

### WRAP/UI Helps Impact Evaluation

The WRAP and UI Helps evaluation will examine savings rates and comprehensiveness of installations in participant homes for both electric and gas measures.    The contract has been awarded to KEMA.  Three challenges have arisen in the early going.   It has been very difficult for the Contractor to determine what measures were recommended for installation to assess whether items were removed, never installed, or rejected by the owner (landlord or participant). The Contractor will do more on-site investigation to try to estimate the gaps.  Second, in many cases either the primary heating fuel or the account number for gas customers is missing from the databases.  The Contractor is removing these customers from the sample and replacing them with similar customers.  The large participant base should greatly reduce the potential for bias that one might normally expect from doing so.

Finally, and unsurprisingly, many program participants have moved since participating.  In many cases, the measures will still be in place at the original location.  However appliances owned by the participants probably left with the participants and may now be in another state.  The Contractor will need to replace this portion of the sample.

The contractor has completed (as of December 7) 65 of 92 site visits and expected to have the remaining completed by mid-December; data from ~ 50 sites has been entered.  Lighting loggers were scheduled to remain through December in order to better measure winter peak savings.  Doing so moves the draft report back by 3-4 weeks compared with the original schedule.  NU and CNG billing data have been provided to KEMA

This study will support ISO requirements.

### CFL Saturation and Net to Gross Assessment

On June 1, the Companies were informed that the Department is interested in gaining more information on the extent to which current programs have transformed the market for Compact Fluorescent Lamps.  The scope of work combines and compares the experiences of other states with and without CFL programs, and also collects and analyzes information unique to Connecticut.  The results will inform development of program alternatives to capture remaining potential from common and specialized CFLs.

NMR was selected as Contractor for this project.  On a fast track, NMR has developed a workplan and provided surveys for randomly selected customers and customers known to have purchased NCP program lamps.  The surveys have been completed.  NMR has developed instruments to use for in-home data collection and to elicit from customers the reasoning behind CFL saturation and location selection in about 100 Connecticut homes. Draft reports for both the regional analysis and the Connecticut sub-sample were provided on October 5.  NMR is redrafting portions of the reports and adding information on lamps that may have been distributed through program activities.

# Commercial/Industrial Studies

### Energy Opportunities Impact Study

The Energy Opportunities Impact Evaluation will determine gross energy and demand savings realization rates, gross and net energy and demand savings, summer and winter coincidence factors, load shapes and annual hours of use for prescriptive measures installed through the ECB program. The study anticipates use of on-site metering using data loggers, lighting loggers and hand held fixture wattage measurement devices to estimate these values.  This impact evaluation will look at the EO Program Year of 2008 in the service territories of United Illuminating and Connecticut Light & Power and also produce combined state level results.

KEMA was selected to be the contractor for this study.  The initial kick-off meeting was held on June 2.  To date, the contractor has scheduled and performed site visits at 55 participant projects.  For each site monitored data have been retrieved and data entered.  Savings analysis for approximately 10 non-lighting sites has been completed.

As of the end of November, the Contractor expected to complete data analysis for all sites and generate lighting profiles for the 20 sites that primarily installed lighting measures.

This study will support ISO requirements.

# Regional EM&V Forum – 2009

### Load Shape Study

This regional study collected load shapes developed at other utilities for measures offered in New England, other states on the Eastern Seaboard and some Northwestern States.  In this two phase project, the contractor first assessed whether or not the load shapes reflect situations sufficiently comparable to those in the Northeast to enable us to use them in filings when utility-specific information is not yet available.  In Phase 2 the contractor will devise sampling plans, conduct on-site data collection efforts and analysis to obtain load and savings profiles (starting October 2009) for those identified measures of particular interest in each region.

The Contractor (KEMA) started working on this project on January 10, 2009.  The Phase 1 recommendations were provided on June 1st and reviewed by subcommittee members.  The report identifies existing load shape studies, gaps in data, and options for filling gaps both in the East and the Northwest.

EM&V Forum participants, guided by the EMV subcommittee, were asked to take additional steps of establishing the priority data needs within the Forum in order to finalize a scope of work and RFP for Load shape Project Phase 2.  As a group the membership decided that the highest priority areas for load shape development are for C&I Lighting and Unitary HVAC systems.

### Load Shape Estimation: C&I Lighting

This project involves the creation of a spreadsheet tool that can be used by members of the Regional EM&V Forum to calculate and quantify the hourly savings of efficient lighting measures installed at Commercial and Industrial facilities.

This project is just beginning.  Two contractors provided proposals on January 8th.  Members of the project subcommittee, which includes me, are reviewing the proposals with the expectation that a contractor will be selected on January 13th.

### Load Shape Estimation:  C&I Unitary HVAC

The objective of the study is the development of Unitary HVAC load factor data for every hour of the calendar year. The annual load shape data must also be adaptable to different program participant populations located within the service territories of Forum members;  load shape data will be weather-normalized in order to provide for the calculation of aggregate load shapes that reflect the weather conditions of different Program Administrator customer populations.

A project subcommittee, which includes me, is working towards the completion of an RFP.

### Glossary of Terms and Definitions Project

The project is on schedule, with a first draft of the glossary reviewed by the subcommittee and now undergoing expansion and some revisions.  Selected technical experts as well as all Project Committee co-chairs will be asked to review the second draft.

### C&I Lighting: Measure Persistence of Savings

The purpose of the project is to develop up-to-date impact parameters that describe lighting measure persistence, i.e. in place and operating over multiple (5+) years based on field and survey samples. The project will also develop equipment life estimates from secondary sources (manufacturer reports). The value of this project to sponsors is that commercial lighting is the largest source of savings for most EE providers in the region. Multi-year persistence lends itself to regional study because the research is difficult, expensive, and measures are consistent across locations.

The subcommittee has selected a contractor for this project (KEMA) and a kick off meeting was held on October 16. The original schedule and work scope for this project were modified as a result of subcommittee review of the proposals. The project will now proceed as a phased effort, with the first phase being outreach to Project funders to establish what program data is available to develop the sampling strategy. The project will have several checkpoints at which the subcommittee and contractors can agree to proceed or suspend the effort depending on the availability of program data and the ability to develop an appropriate sample size and strategy. If the project goes its full course, it is expected to extend into 2010.