Viridian

To:	Energy Efficiency Board

From:	Kim Oswald, on Behalf of the CEEB Evaluation Committee

Date: 	September 13, 2010

RE:	Evaluation Committee Status Report – for September 22 Meeting

## Residential Studies

### Home Energy Solutions Impact Evaluation - CT

This study examines the impacts of gas and electric measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study focuses on a billing analysis, where the results parsed into measure types using engineering models. Nexant is the contractor for this evaluation.

The first draft report was delivered on July 26th.  That draft was disorganized and incoherent. While all indications have been that the Contractor understood and provided the results based on the workplan, it is impossible to tell at this point whether or not that is true.  We provided some direction and asked for a new first draft to be provided as quickly as possible.  The Contractor provided a new draft on August 13th.  This second draft was far more cogent and revealed several areas that the Contractor, as well as the reviewer, found deficient.  Representatives of the Companies, EEB consultants and Nexant met on September 9th to discuss the methods and issues.  Additional data will be required to support the additional analysis required.

The issues with reporting add to many existing project delays.  While several delays were beyond the Contractor’s control (data delays, contract issues); none-the-less the composite delay will affect the Companies’ abilities to incorporate results into the Plan.

This study will support ISO requirements.

### WRAP/UI Helps Impact Evaluation

The WRAP and UI Helps evaluation examined savings rates and comprehensiveness of installations in participant homes for both electric and gas measures.    The contract was awarded to KEMA.

A draft Final Report was provided on July 27 and was reviewed by the Evaluation Consultant and the Companies.

KEMA found that, overall, the program ex ante saving were reasonably close to the measured savings. Gas savings were estimated to be far higher than was calculated using the PSD, mainly due to overly conservative estimates in the PSD.  Moreover, on a per participant household basis, energy savings ranged from 9% to 12% of pre-participation usage.  These savings are in line with those of some of the strongest programs known to the KEMA team.

For some measures, savings were quite different than were anticipated.  The major issue was found to be substantial removal of CFLs (~ 40%).  Since CFLs provide about 60% of the anticipated program savings, their removal moved the overall realization rate to 69% (annual kWh).  There is no indication that CFLs are not being installed; rather that removals are rampant for reasons as yet unknown.  Persistence figures for CFLs in the PSD are based on a study that did not include any limited income not any direct install lamps; it is quite likely that low income customers in programs such as these behave differently from the assumptions in that study.

KEMA made many recommendations for changes to the PSD and to Company procedures. Because the number, I refer to the document rather than reproducing them here.  The recommendations are found on pages E-10 to E-14.

This study will support ISO requirements.

### Social Marketing Behavioral Pilot Program

The RFP for CL&P’s residential and small Behavior Pilot program was released to a list of potential bidders on September 16th.  Proposals are due back to me on October 11th.

The RFP provides for examination of the experimental program design over a period of at least a year and with provision for continuation for 3 years.  In addition, bidders were asked to assume that they would be evaluating the program gas customers in the near future.

United Illuminating is also initiating their program, which has a design quite different from CL&P’s.  In that design, customers will ‘opt in,’ that is to decide actively to participate in the program.  My understanding of the issues UI would like to address in their initial study is to examine customer feedback on their interaction with the program tools and overall satisfaction with their experience and perceived savings.  I have requested that UI provide additional information on the program design and their expectations for it, and will then develop an RFP for its evaluation.

## Commercial/Industrial Studies

### Energy Opportunities Impact Study

KEMA was selected to be the contractor for this study.  The Energy Opportunities Impact Evaluation will determine gross energy and demand savings realization rates, gross and net energy and demand savings, summer and winter coincidence factors, and annual hours of use for prescriptive measures installed through the EO program. The study uses on-site metering using data loggers, lighting loggers and hand held fixture wattage measurement devices to estimate these values.  This impact evaluation looks at the EO Program Year of 2008.

The study is now complete and went to the Board and Department on July 28th.  Presentation of the results is scheduled for the morning of the October 13 EEB meeting.

This study will support ISO requirements.

### Energy Conscious Blueprint Impact and Process Study

Global Energy Partners, LLC (with their subcontractor, Lime Energy) was chosen to complete the study the ECB study. In order to quantify the benefits of efficient measures installed in C&I facilities through the ECB program,  The program benefits include avoided capacity costs resulting from reduced electric demand during peak hours and avoided energy costs resulting from energy savings during seasonal and on/off-peak periods. In addition to the impact study, changes in the program and in the market made plain the need for a process evaluation that will examine customer benefits realized, comprehensiveness and depth of installations made with and beyond program incentives and effects of individual measures on program performance.

The Kick-Off meeting was held on April 28th with participant data collection and development of study parameters soon thereafter.  As of August 31, 2010, Lime installed loggers at 19 sites associated with 21 measures, removed loggers from 9 sites (11 measures), scheduled installation visits at 4 sites, and scheduled logger removal visits at 9 sites.  In support of the process evaluation, Global has received completed surveys from 29 of the sampled participants with notification that an additional 18 customers have partially completed their responses.

There have been many delays related to getting sufficient participant data.  These delays have led inextricably to delay in installing and completing the metering processes.  Therefore, Global is requesting a one-month extension for the Phase 1 report until December 1.  I believe that is a reasonable request that ensures the most complete data. Moving the Phase 1 report will not impact the Final report dates.

| Event/Deliverable | Due Date | New Due Date | Date Completed | Reasons for Delay |
| --- | --- | --- | --- | --- |
| Final Workplan | 5/15 | - | 8/19/2010 | Fuller participant data needed in order to finalize tasks and costs |
| Procure Company data | Within 4 weeks of contract signature |  | ~ 8/31/2010 | CL&P, in particular held much participant data in paper form. Billing data still outstanding as of 8/31. |
| Sample Design and Customer Selection | Within 10 weeks of contract |  | ~ 8/31/2010 | Very near completion |
| Impact and Process Data Collection Protocols | 6/10 |  | 7/26 | Tasks above took precedence |
| Data Collection | 10/01 |  |  |  |
| Phase 1 Report | 11/01 | 12/01 |  | Combined delays |

### Impact Evaluation of the O&M Services

A 2010 impact evaluation of the O&M Services Program was provided for in the 2010 evaluation plan.  Several months ago, I developed a draft RFP for that study on which the Companies provided comment.  This project has been dropped for 2010 mainly because the suggestions of PAs were that this really needs to focus on Retrocommissioning rather than O&M services.  The re-purposed study is included in the 2011 plan.

The study will provide savings data in order to quantify the benefits that process improvements in commercial and industrial (C&I) facilities provide. The benefits may include avoided capacity and energy costs resulting from energy savings during seasonal and on/off-peak periods. In addition, because operations adjustments may not be maintained, persistence is a particular concern for this study.

Beyond the impacts of the current program, it is hoped that this study can inform the evolution of the program through the Business Sustainability Challenge.

### Study of Customer Awareness of the CEEF Programs

The CT Department of Public Utility Control has ordered the Board to determine the extent to which residential, commercial, and industrial customers are aware of and understand that efficiency programs available to them are supplied and paid for by the CEEF and not by the public utilities. Awareness of the programs provided will also be measured.  This study is designed to provide a baseline.  The study was ordered to be produced by June 1; however that date would not have been possible.  Opinion Dynamics was selected to be the contractor on this study.  The Kick-off meeting was held on June 28.

A draft or the residential section of the report has been provided and the need for some additional analysis requested from the Contractor.  A C&I section is expected on September 21st.  I have impressed upon the Contractor the importance of finalizing the report prior to our Plan filing deadline and they have committed to doing so.

## Regional EM&V Forum – 2010

### Load Shape Study – Phase 1 Completed

This regional study collected load shapes developed at other utilities for measures offered in New England, other states on the Eastern Seaboard and some Northwestern States.  In this two phase project, the contractor first assessed whether or not the load shapes reflect situations sufficiently comparable to those in the Northeast to enable us to use them in filings when utility-specific information is not yet available.  In Phase 2 the contractor will devise sampling plans, conduct on-site data collection efforts and analysis to obtain load and savings profiles (starting October 2009) for those identified measures of particular interest in each region.

The Contractor (KEMA) started working on this project on January 10, 2009.  The Phase 1 recommendations were provided on June 1st and reviewed by subcommittee members.  The report identifies existing load shape studies, gaps in data, and options for filling gaps both in the East and the Northwest.

EM&V Forum participants, guided by the EMV subcommittee, were asked to take additional steps of establishing the priority data needs within the Forum in order to finalize a scope of work and RFP for Load shape Project Phase 2.  As a group the membership decided that the highest priority areas for load shape development are for C&I Lighting and Unitary HVAC systems.  See Below.

### Load Shape Estimation: C&I Lighting

This project involves the creation of a spreadsheet tool that can be used by members of the Regional EM&V Forum to calculate and quantify the hourly savings of efficient lighting measures installed at Commercial and Industrial facilities.  The tool will generate 8760 commercial/industrial lighting load shapes (largely from secondary sources). KEMA was selected to complete the study.  For the Commercial Lighting study, NEEP extends thanks to Western Massachusetts Electric, Connecticut Light and Power, and United Illuminating for underwriting

the costs required to make their recent lighting evaluation data usable for this project. Assembling the available data is nearly complete, and the spreadsheet tool design is being coordinated with the Unitary HVAC study.

### Load Shape Estimation:  C&I Unitary HVAC

The objective of the study is the development of Unitary HVAC load factor data for every hour of the calendar year. The annual load shape data must also be adaptable to different program participant populations located within the service territories of Forum members; load shape data will be weather-normalized in order to provide for the calculation of aggregate load shapes that reflect the weather conditions of different Program Administrator customer populations.

The Unitary HVAC Loadshape RFP was issued on January 14, with bids due on January 29. The subcommittee reviewed the HVAC bids on February 4.  The contractor selected was KEMA and the project initiated immediately. For the Unitary HVAC study, data collection is underway and metering will continue through the end of September in order to capture the end of the cooling season. KEMA has also developed a draft spreadsheet tool and information about the econometric model that is being reviewed by advisor Steve Waite and the subcommittee.

### C&I Lighting: Measure Persistence of Savings

The purpose of the project is to develop up-to-date impact parameters that describe lighting measure persistence, i.e. in place and operating over multiple (5+) years based on field and survey samples. The project will also develop equipment life estimates from secondary sources (manufacturer reports). The value of this project to sponsors is that commercial lighting is the largest source of savings for most EE providers in the region. Multi-year persistence lends itself to regional study because the research is difficult, expensive, and measures are consistent across locations.

KEMA is working this study. The original schedule and work scope for this project were modified as a result of subcommittee review of the proposals. The project will now proceed as a phased effort, with the first phase being outreach to Project funders to establish what program data is available to develop the sampling strategy.

KEMA has developed the sample design for this project, based on data collected from EM&V Forum members in New England and New York. The results of this project are expected to deliver measure life estimates developed from models informed by primary data collected from programs that have been in existence and measures that have been installed for many years.

The project schedule has been extended to accommodate a change in available program data. Onsite data collection is one-third complete, and data analysis will take place this fall/winter, with a final report expected in early 2011.

### Common EM&V Methods and Savings Assumptions

As reported by NEEP, “The results of this project will inform two national M&V protocol discussions. The North American Energy Standards Board (NAESB) is currently convening subcommittees for its M&V project to address retail and wholesale M&V for energy efficiency. NEEP gave a presentation at a November NAESB meeting about how the EM&V Methods project can help inform NAESB’s efforts, and 2010 EM&V Forum funding will be used for NEEP to actively participate in the NAESB M&V project throughout the year. The National Action Plan for Energy Efficiency (NAPEE) is also engaged in a national EM&V project. NAPEE has conducted surveys to identify national EM&V needs and priorities and is working with a Technical Resource Group that includes many Forum participants to help focus its efforts. The findings from the EM&V Methods project will help inform the NAPEE project as it further refines the EM&V priority areas to be addressed on a national level.  A final report and guidelines from Project A2: EM&V Methods will be available in mid-2010.”

NEEP presented the report for adoption by its Steering Committee in late May and the guidelines were adopted by consensus.

Common EE Reporting Guidelines

The overall purpose of this study is to address a growing need and interest in consistent reporting of electric and natural gas energy-efficiency program savings, costs and emission impacts across states in the region to help inform multiple energy and environmental policies, including:

- Climate change goals and air quality emission reductions, and associated planning;

- State procurement policies, energy-efficiency savings and associated economic goals; and

- Regional energy planning and forecasting purposes.

NEEP is incorporating revisions and definitions to the draft Guidelines with guidance from lead subcommittee members. The supporting NMR Group team report is complete. NEEP is coordinating with the Glossary Update project to ensure that terms in the Common Reporting Guidelines are appropriately defined in Version 2 of the Glossary. NEEP will circulate the revised final draft Guidelines in early September to all Forum participants, and request comments by September 13 so that NEEP staff can brief the Steering Committee at its quarterly meeting on September 15 on any outstanding issues to be addressed. NEEP anticipates the Guidelines will be presented to the Steering Committee for adoption later this year.  NEEP recently gave a presentation based on this project at the ACEEE Summer Study that addressed the reporting and data needs to support achieving air quality and climate change objectives.

### Incremental Cost Study

Background materials provided by VEIC have been submitted to the subcommittee for development of an RFP.  Using this background, Committee members have drafted an RFP currently being reviewed.  The objectives of the Project are to develop electric and gas

efficient measure incremental cost assumptions for a variety of gas and electric efficiency measures for the region, based on primary and secondary research as appropriate. The RFP proposes residential and small commercial heating and cooling measures as the priority measures. The results of the study will improve the ability of efficiency program planners, program administrators, program evaluators and regulators to: retrospectively assess program cost-effectiveness; prospectively estimate potential program cost-effectiveness to inform which

measures and/or programs should be part of efficiency program portfolios; and inform program design, particularly financial incentive levels.

The Request for Proposal (RFP) for this project was issued in early August, and proposals are due on September 8. The objective of the project is to develop electric and gas efficient measure incremental cost assumptions for a variety of gas and electric efficiency measures for the region, based on primary and secondary research as appropriate. The project subcommittee will review bids and select a contractor in September, and work will begin this fall.

### Impact of Codes and Standards on Advancing Energy Efficiency

The schedule and scope of this project is being proposed to accommodate several recent developments that are relevant to this project topic, including:

- The DPUC Order in to begin examining development of a mechanism for attribution of savings from codes and standards;

- The precedent of regulatory approval that now exists in California to claim savings from codes and standards activities;

- Forum coordination with Massachusetts program administrators to leverage their significant progress in developing a mechanism to claim and attribute savings for residential building energy code compliance and/or improvements related to newly adopted stretch codes;

- Recognition of an interest and need to make regulatory staff and program administrators throughout the region aware (at a high level) of the codes and standards activities and attribution strategies that are ongoing before a more complex or comprehensive regional research project is scoped by the Forum;

The overarching goal of this EMV Forum project is provide and develop a Workshop to assist Forum members whose organizations are a) planning or considering programs and/or other activities that encourage improved codes, standards, and code compliance, and b) expecting to claim savings attributable to their activities.

The workshop is intended to provide information and opportunities for discussion on:

- Types of activities to improve codes, standards;

- Evaluation activities/likely mechanisms and their pros and cons and information needs;

- Similarities and differences between states/programs;

- Regulatory considerations on savings attributable from codes and standards such as barriers to and strategies for obtaining regulatory approval.

Workshop Details

Codes & Standards Workshop—September 28 in Marlborough, Massachusetts

The EM&V Forum and NEEP Policy team are holding a Roadmap to Claiming Energy Savings from Building Codes and Appliance Standards workshop from 9:30am-4:00pm on Tuesday, September 28 in Marlborough, MA at the Courtyard by Marriott.

The workshop provides an opportunity for regulators, program administrators and other energy efficiency stakeholders in the Northeast to interact and learn about ongoing codes and standards policies, programs and evaluation plans, with the goal of helping the region achieve more aggressive savings goals and claim benefits associated with building energy codes and appliance standards.  There is no charge to attend the workshop, but please register as space is limited. In person attendance is strongly encouraged, however, a GoTo Meeting link to view presentations

and a dial-in number will be provided for those who would like to participate remotely.

NEEP has arranged a reduced rate of $119 per night at the Courtyard by Marriott for workshop attendees. In order to guarantee this rate, hotel reservations must be made by September 7. Please reference NEEP when making your reservation.

### Survey of Net Savings Methods

NMR Group, Inc., the contractor for this project, has delivered the work plan resulting from the kick off meeting held in early March. This project will generate a white paper by August 2010, based on secondary research and in-depth interviews with experts and input from subcommittee members. The goal of the paper is to inform and support the EM&V Forum goals of understanding the reasons for measuring net savings, increasing the consistency and quality in EM&V practices with respect to defining and estimating energy efficiency program net savings, and identifying the needs of some related stakeholders (e.g. air regulators) vis-à-vis net savings.

### Natural Gas EE Research and Evaluation

NEEP will be convening a subcommittee this month and scheduling a kick-off call to identify and begin scoping the 2010 natural gas efficiency research project, which will focus on residential and/or C&I gas program research on one or more priority end-uses.  These may include on-demand water heating impact estimation, early retirement of furnaces, gas/solar thermal DHW, and/or building envelope impacts.

### 2011 EM&V FORUM DRAFT LIST OF POTENTIAL PROJECTS (per EM&V Forum)

This is a preliminary list of possible projects. The intention is not to conduct ALL of these activities, but to determine level of interest and prioritize with Forum Participants:

#### Protocol Development

- Net Savings Project – Develop Common Methods/Approaches based on recommendations from Scoping Study (2010 carry over project)

- EMV Methods Guidelines Phase 2 (2010 project moved to 2011). Could address:

  - Emerging technologies (current scope)

  - Use of secondary data

  - Single data parameter studies (e.g. hours of use)

  - Integration of EE and load management/smart grid

  - Use of Deemed Savings

  - Methods/reporting to support private financing needs

  - Baseline Methods – more detailed than what was developed for A2

- Integrating EE into System Planning Guidelines (2010 project moved to 2011)

- Common EE Reporting cont. – support for state implementation of A3 Guidelines

- Data Collection Protocols - to support sharing of metered data

- Develop Common Cost-effectiveness Test(s) to Address New/Emerging EE Programs and Policies

- Forum Product Updates:

  - Glossary of Terms & Acronyms

  - Mid-Atlantic TRM (late 2011)

  - EM&V Savings Assumptions Guidelines

#### Research & Evaluation

- Loadshape research cont. – primary research for next set of priority measures

- Natural Gas research cont.

- Incremental Cost research cont. – next set of priority measures

- Sub-region projects

  - Other measure persistence projects

  - Baseline research

DPUC Review Of The Connecticut Energy Efficiency Fund's 2010 Conservation And Load Management Plan For 2010, Docket No. 09-10-03, pp. 61-63.