Viridian

To:	Energy Efficiency Board

From:	Kim Oswald, on Behalf of the CEEB Evaluation Committee

Date: 	October 7, 2010

RE:	Evaluation Committee Status Report – for October 13 Meeting

__________________________________________________________________________

Residential Studies

Home Energy Solutions Impact Evaluation - CT

This study examines the impacts of gas and electric measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study focuses on a billing analysis, where the results parsed into measure types using engineering models. Nexant is the contractor for this evaluation.

The first draft report was delivered on July 26th and was not within reach of acceptability.  We are now at the 3rd draft.  The report is now in a form where the methods are clearly written and understandable.  Unfortunately, that clarity makes plain that improvements continue to be needed. The issues with reporting add to many existing project delays.  While several delays were beyond the Contractor’s control (data delays, contract issues); none-the-less the composite delay makes it impossible for the Companies to incorporate results into the Plan.

This study will support ISO requirements.

WRAP/UI Helps Impact Evaluation

The WRAP and UI Helps evaluation examines savings rates and comprehensiveness of installations in participant homes for both electric and gas measures.    The contract was awarded to KEMA.

The report is complete.  Presentation is yet to be scheduled.

This study will support ISO requirements.

Residential Behavioral Pilot Program

The RFP for evaluation of CL&P’s behavior pilot program was released for bid on September 16th.  Responses from bidders are due October 11th.  At least 4 proposals are expected.

The original expectation was for a single evaluation of both UI and CL&P’s programs. However, UI has decided to pursue a different model for their Pilot.  I requested, verbally and by email, that UI send information on how their Pilot will be conducted.  While it is now well known that the UI program will be ‘opt in,’ I have not yet received the additional information necessary to develop an evaluation plan. At this point, it is likely that the UI program will be evaluated through a separate study.

Commercial/Industrial Studies

Energy Opportunities Impact Study

KEMA was selected to be the contractor for this study.  The Energy Opportunities Impact Evaluation estimated gross energy and demand savings realization rates, gross and net energy and demand savings, summer and winter coincidence factors, and annual hours of use for prescriptive measures installed through the EO program. The study uses on-site metering using data loggers, lighting loggers and hand held fixture wattage measurement devices to estimate these values.  This impact evaluation looks at the EO Program Year of 2008.

The study is now complete and went to the Board and Department on July 28th.  Presentation of the results is scheduled for the morning of the October 13 EEB meeting.

This study will support ISO requirements.

Energy Conscious Blueprint Impact and Process Study

Global Energy Partners, LLC (with their subcontractor, Lime Energy) was chosen to complete the study the ECB study. In order to quantify the benefits of efficient measures installed in C&I facilities through the ECB program. The program benefits include avoided capacity costs resulting from reduced electric demand during peak hours and avoided energy costs resulting from energy savings during seasonal and on/off-peak periods. In addition to the impact study, changes in the program and in the market made plain the need for a process evaluation that will examine customer benefits realized, comprehensiveness and depth of installations made with and beyond program incentives and effects of individual measures on program performance.

The Kick-Off meeting was held on April 28th with participant data collection and development of study parameters soon thereafter.  As of October 5, 2010, Lime has installed loggers at 49 sites associated with 69 measures, removed loggers from 20 sites, scheduled installation visits at 11 sites, and scheduled logger removal visits at 29 sites.  Summer weather-sensitive metering is complete.

In support of the process evaluation, Global has received completed surveys from 50 of the sampled participants with notification that an additional 33 customers have partially completed their responses. Global is working to convert those partials into completes.

There have also been some delays. Billing data from CL&P has been slow to become available.  In addition, many of the project files from both Companies lack building floor area and other information on how energy impacts were estimated (especially for non-lighting measures). In some cases, the files lack inventories of replaced equipment. This information is necessary for accurate impact analysis though billing simulation modeling.

| Event/Deliverable | Due Date | New Due Date | Date Complete | Reasons for Delay |
| --- | --- | --- | --- | --- |
| Final Workplan | 5/15 | - | 8/19/ | Fuller participant data needed in order to finalize tasks and costs |
| Procure Company data | Within 4 weeks of contract signature |  | ~ 8/31/ | CL&P, in particular held much participant data in paper form. Billing data still outstanding as of 10/5. |
| Sample Design and Customer Selection | Within 10 weeks of contract |  | ~ 8/31/ |  |
| Impact and Process Data Collection Protocols | 6/10 |  | 7/26 | Tasks above took precedence |
| Data Collection (summer weather sensitive) | 10/01 |  | 10/01 |  |
| Process and remaining impact | 11/01 |  |  |  |
| Phase 1 Data Analysis and Report | 11/01 | 12/01 |  |  |

Impact Evaluation of the Retro-commissioning/O&M Services Program

Earle Taylor on behalf of CL&P and I completed a re-draft of an earlier RFP to redirect the emphasis towards important retro-commissioning issues. That draft is currently with the PAs for review. The study will provide savings data in order to quantify the benefits of efficient measures and processes developed in commercial and industrial (C&I) facilities through the O&M Services (O&M) program. The benefits include avoided capacity and energy costs resulting from energy savings during seasonal and on/off-peak periods. In addition, because operations adjustments may not be maintained, persistence is a particular concern for this study. Beyond the impacts of the current program, it is hoped that this study can inform the evolution of the program through the Business Sustainability Challenge.

It is my understanding that NU has recently issued new directive for Purchasing and Legal review of all RFPs prior to their release.  All involved are hoping that this doesn’t delay start-up for the study.

Study of Customer Awareness of the CEEF Programs

The CT Department of Public Utility Control has ordered the Board to determine the extent to which residential, commercial, and industrial customers are aware of and understand that efficiency programs available to them are supplied and paid for by the CEEF and not by the public utilities. Awareness of the programs provided will also be measured.  This study is designed to provide a baseline.  The study was ordered to be produced by June 1; however that date would not have been possible.  Opinion Dynamics was selected to be the contractor on this study.  The Kick-off meeting was held on June 28.

The contractor is now running final numbers and writing the report.

Regional EM&V Forum – 2010

Load Shape Estimation: C&I Lighting

This project involves the creation of a spreadsheet tool that can be used by members of the Regional EM&V Forum to calculate and quantify the hourly savings of efficient lighting measures installed at Commercial and Industrial facilities.  The tool will generate 8760 commercial/industrial lighting load shapes (largely from secondary sources). KEMA was selected to complete the study.  For the Commercial Lighting study, NEEP extends thanks to Western Massachusetts Electric, Connecticut Light and Power, and United Illuminating for underwriting

the costs required to make their recent lighting evaluation data usable for this project. Assembling the available data is nearly complete, and the spreadsheet tool design is being coordinated with the Unitary HVAC study.

Load Shape Estimation:  C&I Unitary HVAC

The objective of the study is the development of Unitary HVAC load factor data for every hour of the calendar year. The annual load shape data must also be adaptable to different program participant populations located within the service territories of Forum members; load shape data will be weather-normalized in order to provide for the calculation of aggregate load shapes that reflect the weather conditions of different Program Administrator customer populations.

The Unitary HVAC Load Shape RFP was issued on January 14, with bids due on January 29. The subcommittee reviewed the HVAC bids on February 4.  The contractor selected was KEMA and the project initiated immediately. For the Unitary HVAC study, data collection is underway and metering will continue through the end of September in order to capture the end of the cooling season. KEMA has also developed a draft spreadsheet tool and information about the econometric model that is being reviewed by advisor Steve Waite and the subcommittee.

C&I Lighting: Measure Persistence of Savings

The purpose of the project is to develop up-to-date impact parameters that describe lighting measure persistence, i.e. in place and operating over multiple (5+) years based on field and survey samples. The project will also develop equipment life estimates from secondary sources (manufacturer reports). The value of this project to sponsors is that commercial lighting is the largest source of savings for most EE providers in the region. Multi-year persistence lends itself to regional study because the research is difficult, expensive, and measures are consistent across locations.

KEMA is working this study. The original schedule and work scope for this project were modified as a result of subcommittee review of the proposals. The project will now proceed as a phased effort, with the first phase being outreach to Project funders to establish what program data is available to develop the sampling strategy.

KEMA has developed the sample design for this project, based on data collected from EM&V Forum members in New England and New York. The results of this project are expected to deliver measure life estimates developed from models informed by primary data collected from programs that have been in existence and measures that have been installed for many years.

The project schedule has been extended to accommodate a change in available program data. Onsite data collection is one-third complete, and data analysis will take place this fall/winter, with a final report expected in early 2011.

Common EM&V Methods and Savings Assumptions

NEEP presented the report for adoption by its Steering Committee in late May and the guidelines were adopted by consensus.

Common EE Reporting Guidelines

The overall purpose of this study is to address growing interest in consistent reporting of electric and natural gas energy-efficiency program savings, costs and emission impacts across states in the region to help inform multiple energy and environmental policies, including:

- Climate change goals and air quality emission reductions, and associated planning;

- State procurement policies, energy-efficiency savings and associated economic goals; and

- Regional energy planning and forecasting purposes.

NEEP is incorporating revisions and definitions to the draft Guidelines with guidance from lead subcommittee members. The supporting NMR Group team report is complete. NEEP is coordinating with the Glossary Update project to ensure that terms in the Common Reporting Guidelines are appropriately defined in Version 2 of the Glossary. NEEP staff briefed the Steering Committee at its quarterly meeting on September 15 on outstanding issues to be addressed. The Steering Committee requested modifications of the guidelines to: include savings impacts from fuels other than electric and gas (e.g., oil, propane); allow for inclusion of savings from efficiency activities funded through sources other than ratepayer funds; and allow for inclusion of demand response program impacts.

Incremental Cost Study

The objective of this Project is to develop incremental cost assumptions for a variety of efficiency measures.  Navigant is the contractor selected for this project.  A kick-off meeting was held on October 8th.

Priority measures:  NEEP and the Subcommittee have developed a list of priority measures on which to focus.

Top Priority Measures

- Residential central air conditioners

- Residential air source heat pumps

- Residential gas furnaces

- Residential furnace fans (e.g. ECM fans)

- Commercial unitary air conditioners

- Commercial boilers

- Residential insulation upgrades (attic, wall, basement)

- Residential air sealing

Second Priority Measures

- Large commercial HVAC measures (e.g. chillers)

- Variable Frequency Drives

- Ductless mini-splits (residential and commercial applications)

Final decisions on the scope of work and workplan will be forthcoming over the next few weeks.

Impact of Codes and Standards on Advancing Energy Efficiency

The schedule and scope of this project is being proposed to accommodate several recent developments that are relevant to this project topic, including:

- The DPUC Order in to begin examining development of a mechanism for attribution of savings from codes and standards;

- The precedent of regulatory approval that now exists in California to claim savings from codes and standards activities;

- Forum coordination with Massachusetts program administrators to leverage their significant progress in developing a mechanism to claim and attribute savings for residential building energy code compliance and/or improvements related to newly adopted stretch codes;

- Recognition of an interest and need to make regulatory staff and program administrators throughout the region aware (at a high level) of the codes and standards activities and attribution strategies that are ongoing before a more complex or comprehensive regional research project is scoped by the Forum;

The overarching goal of this EMV Forum project is provide and develop a Workshop to assist Forum members whose organizations are a) planning or considering programs and/or other activities that encourage improved codes, standards, and code compliance, and b) expecting to claim savings attributable to their activities.

The workshop is intended to provide information and opportunities for discussion on:

- Types of activities to improve codes, standards;

- Evaluation activities/likely mechanisms and their pros and cons and information needs;

- Similarities and differences between states/programs;

- Regulatory considerations on savings attributable from codes and standards such as barriers to and strategies for obtaining regulatory approval.

Survey of Net Savings Methods

NMR Group, Inc., the contractor for this project, has delivered the work plan resulting from the kick off meeting held in early March. This project will generate a white paper by August 2010, based on secondary research and in-depth interviews with experts and input from subcommittee members. The goal of the paper is to inform and support the EM&V Forum goals of understanding the reasons for measuring net savings, increasing the consistency and quality in EM&V practices with respect to defining and estimating energy efficiency program net savings, and identifying the needs of some related stakeholders (e.g. air regulators) vis-à-vis net savings.

Natural Gas EE Research and Evaluation

NEEP will be convening a subcommittee this month and scheduling a kick-off call to identify and begin scoping the 2010 natural gas efficiency research project, which will focus on residential and/or C&I gas program research on one or more priority end-uses.  These may include on-demand water heating impact estimation, early retirement of furnaces, gas/solar thermal DHW, and/or building envelope impacts.

DPUC Review Of The Connecticut Energy Efficiency Fund's 2010 Conservation And Load Management Plan For 2010, Docket No. 09-10-03, pp. 61-63.