Viridian

To:	ECMB

From:	Kim Oswald, on Behalf of the ECMB Evaluation Committee

Date: 	November 17, 2009

RE:	Evaluation Committee Status Report – for November 18 meeting

# Residential Studies

#### Demand and Energy Savings in Residential Lighting – Regional – Complete 1/30/09 This study will support ISO requirements.

#### Ductless Heat Pumps: Energy and Demand Savings; Customer Satisfaction – Regional – Complete 7/22/09

#### Residential Central Air Conditioning – Regional - Complete

The Residential CAC study was intended to examine load shapes, coincidence factors and savings from various CAC measures.  This study is being done within the regional Evaluation Working Group.  The current contract is produce summer usage profiles for replacement air conditioners.

ADM Associates was selected to complete the study.  After numerous problems, errors and delays, the Contractor has produced a final report that is acceptable.  In addition to working on the savings impacts of the programs, Connecticut issued a separate contract to assess free-ridership.  Both reports are complete and available for filing.

This study is intended to support ISO requirements.

#### Home Energy Solutions Impact Evaluation - CT

This study will examine the impacts of gas and electric measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study will focus primarily on measures or groups of measures with the largest savings potential and that also have not been examined through other studies.

Nexant has been selected as contractor for this evaluation.  The kickoff meeting was held on May12. Currently, the Contractor has formed the sample using a review of the program records to determine an appropriate sampling frame. Currently, Nexant has completed 26 of 31 site visits in the CL&P service area and are now collecting customer billing data for participants and a matched sample of non-participants.  The contractor has also sent letters to about 40 UI area customers, from which 9 will be selected for site visits. Billing data collection in the UI service area is beginning.

This study will support ISO requirements.

### Residential New Construction Standard Practice - CT

This CT study has been moved to 2011 at this time due to extreme reductions in new housing permits.  When conducted, the study is expected to examine how builders typically incorporate efficiency measures in residential buildings constructed both within and outside of Energy Star program activities.  The study would incorporate surveys and interviews with builders and contractors to examine current building practice.  Site visits would be used to verify reported building practices.

#### WRAP/UI Helps Impact Evaluation

The WRAP and UI Helps evaluation will examine savings rates and comprehensiveness of installations in participant homes for both electric and gas measures.    The contract has been awarded to KEMA.  Three challenges have arisen in the early going.   It has been very difficult for the Contractor to determine what measures were recommended for installation to assess whether items were removed, never installed, or rejected by the owner (landlord or participant). The Contractor will do more on-site investigation to try to estimate the gaps.  Second, in many cases either the primary heating fuel or the account number for gas customers is missing from the databases.  The Contractor is removing these customers from the sample and replacing them with similar customers.  The large participant base should greatly reduce the potential for bias that one might normally expect from doing so.  Finally, and unsurprisingly, many program participants have moved since participating.  In many cases, the measures will still be in place at the original location.  However appliances owned by the participants probably left with the participants and may now be in another state.  The Contractor will need to replace this portion of the sample.  The contractor has completed 41 of 92 site visits and expects to have the remaining completed by early December.  Lighting loggers will remain through December in order to better measure winter peak savings.  Doing so will move the draft report back by 3-4 weeks.

This study will support ISO requirements.

#### CFL Saturation and Net to Gross Assessment

On June 1, the Companies were informed that the Department is interested in gaining more information on the extent to which current programs have transformed the market for Compact Fluorescent Lamps.  The scope of work combines and compares the experiences of other states with and without CFL programs, and also collects and analyzes information unique to Connecticut.  The results will inform development of program alternatives to capture remaining potential from common and specialized CFLs.

NMR was selected as Contractor for this project.  On a fast track, NMR has developed a workplan and provided surveys for randomly selected customers and customers known to have purchased NCP program lamps.  The surveys have been completed.  NMR has developed instruments to use for in-home data collection and to elicit from customers the reasoning behind CFL saturation and locational selection in about 100 Connecticut homes. Draft reports for both the regional analysis and the Connecticut sub-sample were provided on October 5.

#### eeSmarts Evaluation – CT  The project is now completed.

# Commercial/Industrial Studies

### Small Business Energy Advantage Impact Evaluation - CT

The report was completed and accepted for filing on August 24, 2009.  This study will support ISO requirements.

### C&I Spillover and Free-Ridership Study – Regional.  The project is now completed.

### Energy Opportunities Impact Study

The Energy Opportunities Impact Evaluation will determine gross energy and demand savings realization rates, gross and net energy and demand savings, summer and winter coincidence factors, load shapes and annual hours of use for prescriptive measures installed through the ECB program. The study anticipates use of on-site metering using data loggers, lighting loggers and hand held fixture wattage measurement devices to estimate these values.  This impact evaluation will look at the EO Program Year of 2008 in the service territories of United Illuminating and Connecticut Light & Power and also produce combined state level results.

KEMA was selected to be the contractor for this study.  The initial kick-off meeting was held on June 2.  The contractor is in the process of receiving program data and has developed a final sample plan based on the analysis of that data.  The Evaluation Consultant and the Companies decided that adding a few additional sites would better enable us to meet ISO-NE precision guidelines and that change has been incorporated into the workplan.  Field data collection is beginning.   This study will support ISO requirements.

# Regional EM&V Forum – 2009

### Load Shape Study

This regional study collected load shapes developed at other utilities for measures offered in New England, other states on the Eastern Seaboard and some Northwestern States.  In this two phase project, the contractor first assessed whether or not the load shapes reflect situations sufficiently comparable to those in the Northeast to enable us to use them in filings when utility-specific information is not yet available.  In Phase 2 the contractor will devise sampling plans, conduct on-site data collection efforts and analysis to obtain load and savings profiles (starting October 2009) for those identified measures of particular interest in each region.

The Contractor (KEMA) started working on this project on January 10, 2009.  The Phase 1 recommendations were provided on June 1st and reviewed by subcommittee members.  The report identifies existing load shape studies, gaps in data, and options for filling gaps both in the East and the Northwest.

EM&V Forum participants, guided by the EMV subcommittee, were asked to take additional steps of establishing the priority data needs within the Forum in order to finalize a scope of work and RFP for Load shape Project Phase 2.  As a group the membership decided that the highest priority areas for load shape development are for C&I Lighting and Unitary HVAC systems.  Work on the RFPs for Phase 2 is ongoing as a facilitated subcommittee effort.

### Glossary of Terms and Definitions Project

The project is on schedule, with a first draft of the glossary reviewed by the subcommittee and now undergoing expansion and some revisions.  Selected technical experts as well as all Project Committee co-chairs will be asked to review the second draft.

### C&I Lighting Measure Persistence of Savings

The purpose of the project is to develop up-to-date impact parameters that describe lighting measure persistence, i.e. in place and operating over multiple (5+) years based on field and survey samples. The project will also develop equipment life estimates from secondary sources (manufacturer reports). The value of this project to sponsors is that commercial lighting is the largest source of savings for most EE providers in the region. Multi-year persistence lends itself to regional study because the research is difficult, expensive, and measures are consistent across locations.

The subcommittee has selected a contractor for this project (KEMA) and a kick off meeting was held on October 16. The original schedule and work scope for this project were modified as a result of subcommittee review of the proposals. The project will now proceed as a phased effort, with the first phase being outreach to Project funders to establish what program data is available to develop the sampling strategy. The project will have several checkpoints at which the subcommittee and contractors can agree to proceed or suspend the effort depending on the availability of program data and the ability to develop an appropriate sample size and strategy. If the project goes its full course, it is expected to extend into 2010.