Viridian

To:	ECMB

From:	Kim Oswald, on Behalf of the ECMB Evaluation Committee

Date: 	March 5, 2008

RE:	Evaluation Committee Status Report

### Residential Studies

#### Residential Lighting Persistence - Regional

A regional Evaluation Working Group is now conducting a study of the persistence of CFLs placed under direct install programs.  Nexus Market Research is conducting the study.   As of the end of February, all data have been collected, data entry and cleaning is complete, and analysis is on-going.  A draft report is expected in mid-March.

#### Demand and Energy Savings in Residential Lighting - Regional

Since most lighting going into homes both now and in the future is purchased through markdown programs at point of purchase, it is especially difficult to determine (1) who is buying (2) what products (3) installing them in what sockets, if any, and (4) using them for how many hours per day.  This study will develop an initial sample and develop means for the program managers and/or evaluators to continue developing samples.  Then the study will determine energy savings and coincident demand savings for the lighting installed.  The contract was awarded to a team made up of Nexus Market Research, RLW Analytics and GDS Associates.  A full complement of CFLs has been metered and the evaluation team has submitted an initial report outlining the results of the winter season metering.

In CT, CL&P staff, Gary Elliot, was able to convince 7 “Big Box” stores to allow NMR onsite to interview customers as they purchase CFLs.  We believe that doing so will allow us to examine customer motivations for purchase of those particular bulbs, CFLs in general, planned disposition of the bulbs purchased that day, and marketing related considerations.  We had hoped to convince the regional group to join in to this portion of the study.  However, when the MA utilities were unable to get access to stores in that state, they decided not to participate.  NMR is assessing their proposal in light of scope changes we requested.

#### Ductless Heat Pumps: Energy and Demand Savings; Customer Satisfaction

This regional study is designed to assess results from the Ductless Split Heat Pump pilot programs offered in Massachusetts and Connecticut. NSTAR is managing the project.  RLW Analytics and Nexus Market Research are the contractors for this project, which was kicked-off on December 7, 2007.  As of the end of February, meters have been installed in the winter sample homes and about half of the customer and contractor surveys are complete for the winter phase.  Additional homes will be recruited for an augmented summer sample and the project completed this fall.

#### Residential Central Air Conditioning

I am leading the development of an RFP to examine load shapes, coincidence factors and savings from various CAC measures.  This study will be done within the regional Evaluation Working Group.  During the first year of the study, the study will produce summer usage profiles for replacement air conditioners.  During the second year, additional measures such as tune-ups, duct-sealing, and right-sizing will be examined.  The RFP should be released on March 10.

#### Home Energy Solutions Impact Evaluation

The HES impact study will begin during the summer of 2008 piggybacking on the Residential A/C study described above, but developed to meet the needs of the CT program.   Billing analysis will augment metered information from A/C study to capture the impact of measures installed and services provided throughout the house.

### Commercial/Industrial Studies

#### Standard Practice in C&I Design RFP

RLW was selected to complete this study that focuses on the architects, designers, and suppliers who are important players in the design process to determine: (1) when in the design process efficiency decisions are made (2) what players are most involved in the decisions (3) how the utilities can support efforts to increase efficiency.  The draft report was submitted January 19th.  The initial draft did not provide the needed information.  RLW has a policy of client satisfaction and has augmented their initial analysis and provided a much stronger draft report.  The final report is expected by the end of March.

#### ISO M&V Requirements

A study of ISO M&V standards was initiated in December.  The study is important to the ECMB and to the Companies for assessing savings from the programs offered as resources to the FCM since the ISO standards do not supply clear direction on how monitoring can be completed..  Most of the ISO M&V requirements entail the specifications and compliance of the measurement hardware itself.  The remaining requirements affect the methods by which the equipment and resultant data are employed.  A key component of this project is attaining consensus on a definitive interpretation of these published requirements.

RLW was selected by the regional Evaluation Working Group to conduct this study.    The total, not-to-exceed cost of the project, $24,000 is to be divided between the regional utilities.  Under the costing structure of the regional group, the total cost to UI will be no more than $1,304 and to CL&P, $5,283.  The savings in participating with the Regional Group and the advantages of being able to offer a consensus document to ISO are substantial.

### C&I Spillover and Free-Ridership Study

The Regional Group led by NGRID initiated a study to assess free-rider and spillover factors for the energy efficiency measures and programs offered to the Sponsors’ commercial and industrial customers.  Although the CT Evaluation Plan did not call for such a study until the end of 2008, the financial and bidding advantages of working with the larger group outweighed the disadvantage of moving costs earlier in the year.  PA Consulting was selected to complete the project on January 16th and began immediately.  The resulting study will be complete by the end of the summer of 2008.

By the end of February, all survey instruments were completed and approved.  At this time, customer surveys have been initiated.

#### Unitary HVAC

This Regional study will examine summer peak impact and coincidence factors for Unitary HVAC for FCM purposes.  NGRID has volunteered to write the RFP and manage the project.  However, no individual has yet been identified as having begun the work

#### Omnibus Load Shape Study

This regional study will require a contractor to collect load shapes developed at other utilities for measures offered in New England.  The contractor will assess whether or not the load shapes reflect situations sufficiently comparable to those in New England to enable us to use them in filings when utility-specific information is not yet available.  NEEP has volunteered to lead this study.

#### C&I Measure Persistence of Savings

Tentatively planned for late 2008 (or early 2009), this regional study will examine persistence of savings for measures installed under C&I programs.  Among the issues to be addressed is the question of how changes in business within a given location affect measure persistence and whether such changes as may be found should result in changes in participant targeting or eligibility.  No lead organization or individual has yet been identified.

#### C&I HVAC Peak Impacts and Coincidence

This regional study was developed during the Spring of 2007, but was later shelved due to the lack of time prior to the cooling season.  The study is to be initiated during 2008.

#### Market Opportunities Studies

The 2007 and 2008 Evaluation Plans contain several studies to examine market opportunities in both residential and C&I measures and technologies.  These studies will examine potential lost opportunities, under-utilized and emerging technologies and market approaches to best reach these measures.  Load control opportunities will be developed for the residential and small commercial sectors.  To date, timing for these studies has not been determined; however, the studies are now planned to begin in 2008.