Viridian

To:	ECMB

From:	Kim Oswald, on Behalf of the ECMB Evaluation Committee

Date: 	September 6, 2009

RE:	Evaluation Committee Status Report – for September 9 meeting

The evaluation committee is working on developing protocols to comport with the decision in Docket No. 081003-05-07-09.

# Residential Studies

#### Demand and Energy Savings in Residential Lighting – Regional – Complete 1/30/09 This study will support ISO requirements.

#### Ductless Heat Pumps: Energy and Demand Savings; Customer Satisfaction – Regional – Complete 7/22/09

This regional study is designed to assess results from the Ductless Split Heat Pump pilot programs offered in Massachusetts and Connecticut. NSTAR is managing the project.  RLW Analytics (now part of KEMA) and Nexus Market Research are the contractors for this project. The contractor has completed the final report, which was filed in July.  Presentation date is September 9.

#### Residential Central Air Conditioning - Regional

The Residential CAC study was intended to examine load shapes, coincidence factors and savings from various CAC measures.  This study is being done within the regional Evaluation Working Group.  The current contract is produce summer usage profiles for replacement air conditioners.  If the Sponsors were to elect to add a second year, additional measures such as tune-ups, duct-sealing, and right-sizing would be examined.  At this point, no second year is anticipated.

ADM Associates was selected to complete the first year of the study with an option for Year 2.  There have been many delays to date.   While we expected the project to be complete by October, 2008, ADM indicated that the project would be complete in December.   A first draft was provided on December 31, 2008.  Review of the draft report revealed inappropriate methods and assumptions leading to useless and unstable results.  The Sponsors wrote formal letters to the Contractor, requesting explanation of methods and provision of data as well as reanalysis if indicated.

ADM provided responses to these concerns.  However, since that time, additional problems have been found that may have threatened the validity of the project.  The Sponsors again sent out formal documentation of the deficiencies.  ADM’s next draft of the report was provided on June 9 accompanied by all data and models.  At this time, it appears that the Sponsors’ concerns are likely to be solvable. After additional review and discussion with ADM, the Contractor provided a new draft on August 27.  The Sponsors are reviewing the document at this time.  Some additional concerns have arisen. I hope and expect that the next draft will be final and will be accompanied by the CT free ridership report, which continues to be outstanding.  This study will support ISO requirements.

#### Home Energy Solutions Impact Evaluation - CT

This study will examine the impacts of gas and electric measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study will focus primarily on measures or groups of measures with the largest savings potential and that also have not been examined through other studies.

Nexant has been selected as contractor for this evaluation.  The kickoff meeting was held on May12. Currently, the Contractor has formed the sample using a review of the program records to determine an appropriate sampling frame. They are now collecting customer billing data from participants and non-participants.

There have been some difficulties in getting consistent and usable data from the Companies and contract issues have slowed the study initiation by a substantial amount, but these now appear to be on the way to resolution. This study will support ISO requirements.

### Residential New Construction Standard Practice - CT

This CT study is expected to examine how builders typically incorporate efficiency measures in residential buildings constructed both within and outside of Energy Star program activities.  The first phase of the study is expected to incorporate surveys and interviews with builders and contractors to examine current building practice.  Site visits will be used to verify reported building practices.  A second phase will look more closely at program processes and participation.  A rough draft Scope of Work was developed and circulated on August 24 2008.  As a lower priority study, it has been on hold since then.

We recently learned that the MA utilities expect to conduct a similar study in 2010.  We are currently examining the viability of working with MA.  If so, doing so will allow for larger sample sizes and, possibly, reduced costs.  However, the lack of current construction indicates that it may be best to delay this study until 2011.

#### WRAP/UI Helps Impact Evaluation

The WRAP and UI Helps evaluation will examine savings rates and comprehensiveness of installations in participant homes for both electric and gas measures.    The contract has been awarded to KEMA and the project is beginning with sample development pending execution of final contracts.   This study will support ISO requirements.

#### CFL Saturation and Net to Gross Assessment

On June 1, the Companies were informed that the Department is interested in gaining more information on the extent to which current programs have transformed the market for Compact Fluorescent Lamps.  The scope of work combines and compares the experiences of other states with and without CFL programs, and also collects and analyzes information unique to Connecticut.  The results will inform development of program alternatives to capture remaining potential from common and specialized CFLs.

NMR was selected as Contractor for this project.  On a fast track, NMR has developed a workplan and provided surveys for randomly selected customers and customers known to have purchased NCP program lamps.  The surveys have been completed.  NMR has developed instruments to use  for in-home data collection and to elicit from customers the reasoning behind CFL saturation and locational selection in about 100 Connecticut homes. These site visits are in process. The project will be complete in late October.

#### eeSmarts Evaluation – CT  The project is now completed.

# Commercial/Industrial Studies

### Small Business Energy Advantage Impact Evaluation - CT

The impact evaluation of the SBEA program will determine coincidence factors, energy and demand savings, realization rates and hours of use for prescriptive measures installed through the SBEA Program. The evaluation will involve on-site metering using data loggers, lighting loggers and hand held fixture Wattage measurement devices.

The Cadmus Group was selected to conduct this study.  Project kick-off was on August 29th.

The final report was expected by the end of January 2009; however concerns by NU on how WMECO should be incorporated into the study delayed data collection.  Additional delays were caused by difficulties in scheduling caused by the holidays.  The report was completed and accepted for filing on August 24, 2009.  This study will support ISO requirements.

### C&I Spillover and Free-Ridership Study – Regional.  The project is now completed.

### Energy Opportunities Impact Study

The Energy Opportunities Impact Evaluation will determine gross energy and demand savings realization rates, gross and net energy and demand savings, summer and winter coincidence factors, load shapes and annual hours of use for prescriptive measures installed through the ECB program. The study anticipates use of on-site metering using data loggers, lighting loggers and hand held fixture wattage measurement devices to estimate these values.  This impact evaluation will look at the EO Program Year of 2008 in the service territories of United Illuminating and Connecticut Light & Power and also produce combined state level results.

KEMA was selected to be the contractor for this study.  The initial kick-off meeting was held on June 2.  The contractor is in the process of receiving program data and has developed a final sample plan based on the analysis of that data.  The Evaluation Consultant and the Companies decided that adding a few additional sites would better enable us to meet ISO-NE precision guidelines and that change has been incorporated into the workplan.  Field data collection is beginning.   This study will support ISO requirements.

### Other

### Efficiency and Demand Response Potential Study – CT.   Energy consumption portions of the study are complete.

### Energy Efficiency and Renewable Energy Economy Study. The project is now completed.

# Regional EM&V Forum – 2009

EM&V Forum Presentation to the ECMB

The EM&V Forum Director, Julie Michals, is interested in presenting their 2010 plan to the Board at an upcoming meeting as preferred.

### Load Shape Study

This regional study will require a contractor to collect load shapes developed at other utilities for measures offered in New England.  The contractor will assess whether or not the load shapes reflect situations sufficiently comparable to those in the Northeast to enable us to use them in filings when utility-specific information is not yet available.  Phase 2 - Devise sampling plans, conduct on-site data collection efforts and analysis to obtain load and savings profiles (starting October 2009).

The Contractor (KEMA) started working on this project on January 10, 2009.  The Phase 1 recommendations were provided on June 1st and reviewed by subcommittee members.  Revisions to the draft report are expected from KEMA on or before August 31st. The report identifies existing load shape studies, gaps in data, and options for filling gaps both in the East and the Northwest. EM&V Forum participants, guided by the EMV subcommittee, were asked to take additional steps of establishing the priority data needs within the Forum in order to finalize a scope of work for Load shape Project Phase 2.

Work on the RFP for Phase 2 is ongoing as a facilitated subcommittee effort. The target is to have an RFP released in the fall, a contractor selected in the fall, and any field and other analytical work carried out extending into 2010. This will allow the budget for Phase 2 to exceed the currently limited budget allocation for 2009, and will allow collection of weather-sensitive data to proceed as needed and appropriate.

### Glossary of Terms and Definitions Project

The project is on schedule, with a first draft of the glossary reviewed by the subcommittee and now undergoing expansion and some revisions.  Selected technical experts as well as all Project Committee co-chairs will be asked to review the second draft.

### C&I Lighting Measure Persistence of Savings

The purpose of the project is to develop up-to-date impact parameters that describe lighting measure persistence, i.e. in place and operating over multiple (5+) years based on field and survey samples. The project will also develop equipment life estimates from secondary sources (manufacturer reports). The value of this project to sponsors is that commercial lighting is the largest source of savings for most EE providers in the region. Multi-year persistence lends itself to regional study because the research is difficult, expensive, and measures are consistent across locations.

The subcommittee has selected a contractor for this project and is in the process of finalizing contract arrangements and will be scheduling a kick off meeting. The original schedule and work scope for this project was modified as a result of subcommittee review of the proposals. The project will now proceed as a phased effort, with the first phase being outreach to Project funders to establish what program data is available to develop the sampling strategy. The project will have several checkpoints at which the subcommittee and contractors can agree to proceed or suspend the effort depending on the availability of program data and the ability to develop an appropriate sample size and strategy. If the project goes its full course, it is expected to extend into 2010.

### Common EM&V Methods and Survey Savings Assumptions

This project has two sub-projects:

1.  EM&V Methods Project (2009) This project will collect and review EM&V methods for calculating/determining gross savings, baseline conditions, and measure life/persistence, and develop best practices/guidelines for electric and natural gas energy efficiency program evaluations.

2.  Survey Savings Values, Assumptions and Algorithms (2009). This project will collect and review existing energy and demand savings assumptions (e.g., deemed savings values, input assumptions, and algorithms) for priority end-use measures across region and develop comparative database with categories identifying key differences (e.g., type of program design, different climate zones, etc.).

The RFP for this project has just been released.  The contractor will soon be selected. The total cost to all Sponsors for these 2 sub-projects is estimated to be $320,000.

3.  Develop Common Reporting Guidelines. The RFP for this project was released on August 12, and bids are due September 2. NEEP has received four notices of intent to bid, and will be selecting the winning bidder with the project subcommittee by September 15.

4.  ISO-NE M&V Manual. This July/August, NEEP explored proposed modifications to the metering section of the ISO-NE M&V manual with ISO-NE staff and NEPOOL members, and subsequently decided to defer further action for now. Indications are that there is not an urgent need for New England stakeholders to raise this, given that many other activities are currently the focus of attention for ISO-NE staff, and that the upcoming NAESB energy efficiency M&V project will likely present an opportunity to raise the proposed changes to metering requirement standards in the ISO-NE M&V manual in another related arena.

### Projects for 2010 are now being selected.

These EM&V projects are:

1. Common assumptions or methods

a. Incremental cost assumptions
b. Common savings assumptions – input to PSD
c. Methods to determine job creation impacts of efficiency programs
d. Common cost-effectiveness assessment methods, esp. regarding carbon emission caps
e. Best practices for estimating free-ridership and spillover

2. Impact Evaluations

a. Unitary HVAC
b. Res. New Construction – Impact of changes in codes and standards
c. Measure Life Study

3. Gas Studies

a. Residential Impacts

i.  On demand DHW
ii. Gas or solar thermal DHW
iii. Early replacement of gas furnaces

b. C&I impacts

i. Cooking
ii. Heat recovery
iii. Building shell improvements

4. Market Studies

a. C&I market characterization – baseline conditions and market opportunities

5. Phase II of current studies

I have made recommendations that focus on impact evaluations – especially for Unitary HVAC.  Unitary HVAC impacts are less well known than those of other measures and offer great reward per invested dollar to Connecticut.